## Summary
Project tracker
Status counts and hours come from the Tasks sheet; the red rows there are late.
Status | Tasks | Hours left | Owner | Remaining (h)
Not started | 5 | 120 | Maya | 35.2
In progress | 4 | 46.2 | Omar | 55
Blocked | 1 | 22.4 | Priya | 49.6
Done | 4 | 0 | Lucas | 40.8
|  |  | Ines | 8
Total | 14 | 188.6
Complete | 39.94%
Late tasks | 2
Next due | Data model

## Tasks
ID | Task | Owner | Status | Start | Due | Estimate (h) | Done | Remaining (h) | Days left | Late
T-01 | Kick-off and scope | Ines | Done | 2026-09-01 | 2026-09-03 | 8 | 100% | 0 |  | FALSE
T-02 | User research | Maya | Done | 2026-09-02 | 2026-09-10 | 24 | 100% | 0 |  | FALSE
T-03 | Wireframes | Maya | Done | 2026-09-08 | 2026-09-15 | 20 | 100% | 0 |  | FALSE
T-04 | API design | Omar | Done | 2026-09-08 | 2026-09-14 | 16 | 100% | 0 |  | FALSE
T-05 | Data model | Priya | In progress | 2026-09-12 | 2026-09-22 | 24 | 70% | 7.2 | -6 | TRUE
T-06 | Auth and roles | Omar | In progress | 2026-09-15 | 2026-09-26 | 30 | 50% | 15 | -2 | TRUE
T-07 | Visual design | Maya | In progress | 2026-09-16 | 2026-09-30 | 32 | 40% | 19.2 | 2 | FALSE
T-08 | Import pipeline | Priya | Blocked | 2026-09-18 | 2026-10-02 | 28 | 20% | 22.4 | 4 | FALSE
T-09 | Reporting screens | Omar | Not started | 2026-09-29 | 2026-10-15 | 40 | 0% | 40 | 17 | FALSE
T-10 | Test plan | Lucas | In progress | 2026-09-20 | 2026-09-28 | 12 | 60% | 4.8 | 0 | FALSE
T-11 | Regression suite | Lucas | Not started | 2026-10-05 | 2026-10-20 | 36 | 0% | 36 | 22 | FALSE
T-12 | Performance pass | Priya | Not started | 2026-10-12 | 2026-10-24 | 20 | 0% | 20 | 26 | FALSE
T-13 | Beta release | Ines | Not started | 2026-10-26 | 2026-10-30 | 8 | 0% | 8 | 32 | FALSE
T-14 | Docs and help | Maya | Not started | 2026-10-15 | 2026-10-28 | 16 | 0% | 16 | 30 | FALSE
Formulas:
Days left = IF([Status]="Done","",[Due]-TODAY())
Late = AND([Status]<>"Done",[Due]<TODAY())

## Team
Name | Role | Hours a week | Open tasks | Open hours | Load | Name | Open hours
Maya | Design | 30 | 2 | 35.2 | 58.67% | Maya | 35.2
Omar | Engineering | 40 | 2 | 55 | 68.75% | Omar | 55
Priya | Engineering | 40 | 3 | 49.6 | 62% | Priya | 49.6
Lucas | QA | 35 | 2 | 40.8 | 58.29% | Lucas | 40.8
Ines | Product | 25 | 1 | 8 | 16% | Ines | 8